## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | prodajaautomobili.ba Bug Detecter
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 7.1.2026 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.polovniautomobili.ba" 3. Do not enter anything into the search bar "Pretraži po ključnoj riječi" 4. Click the ENTER button 5. User is shown random number of selling items EXPECTED RESULT: The following sequence of actions should result a warning by the website saying that a user has to give an input before searching SCREENSHOT https://imgur.com/a/ahrXern | [6 empty] | New |  |  |  |  | New
2 | 7.1.2026 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.polovniautomobili.ba" 3. In combo boxes "Godište od" select a year bigger than the one selected at "Godište do" 4. The search will still be active and response will work. EXPECTED RESULT: The result should be a warning to the user informing them that it is not possible for an item to be produced in reverse. SCREENSHOT https://imgur.com/a/Kevto7s | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 7.1.2026 | Tarik Ganić | 1. Open Google Chrome web browser 2. Go to the website www.polovniautomobili.ba 3. Select any car make from the filters 4. Select year of production in the filters 5. Press the search button to display results 6. Change the selected car make or change the year of production 7. Press the search button again After performing two consecutive searches with changed filters, the page can get stuck in a continuous loading loop and does not display the results. EXPECTED RESULT: The page should refresh the results correctly after each filter change, or display a clear error message, instead of getting stuck in a loading loop. SCREENSHOT https://imgur.com/a/sQbVZNh | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 7.1.2026 | Tarik Ganić | 1. Open Google Chrome web browser 2. Go to the website www.polovniautomobili.ba 3. Click on “Prijavi se” (Log in) 4. On the login page, click on “Registruj se” (Register) 5. In the registration form, go to the field for entering the phone number 6. Type any random sequence of characters (letters, symbols, mixed characters) instead of a valid phone number 7. Submit or continue the registration process ACTUAL RESULT: The page accepts any sequence of characters in the phone number field as valid input and does not display any validation error. EXPECTED RESULT: The page should validate the phone number field and display an error message when non-numeric or invalid values are entered, instead of accepting them as valid input. SCREENSHOT https://imgur.com/a/test-4-LI3Uiyr | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 7.1.2026 | Tarik Ganić | 1. Open Google Chrome web browser 2. Go to the website www.polovniautomobili.ba 3. Delete your user account/profile 4. Click on “Prijavi se” 5. Enter the same credentials that were used for the deleted account 6. Confirm login ACTUAL RESULT: The page displays a message stating that the account does not exist. After that, if “Registruj se” (Register) is clicked, the page becomes unresponsive and the user is not able to complete the registration process. EXPECTED RESULT: After deleting the account, the page should allow the user to create a new account without freezing. The registration page should remain responsive and enable successful registration with the previously deleted credentials. SCREENSHOT https://imgur.com/a/f7j5QGl | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | [16 empty] | Closing | Development
7 | [17 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).